## WBS
MKIWMS Development | [7 empty] | Progress | [12 empty] | Yes |  | Note
Updated at: 2026-2-26 | [10 empty] | Plan |  |  |  | Actual
New
STT | Tracker | Priority | Iteration | Features | Functions/Screen | Tasks | Task Detail | Total Man-hours | Man- Hours | Assignee | Develop Start Date | Develop End Date | Review End Date | Progress | Develop Start Date | Develop End Date | Review End Date | Progress | EV | Release Date | Status | 2021-12-14
|  |  | ITERATION 1 (2/2/2026 -28/2/2026) | Common
| 1 |  | 1 | Common Feature | Login | UI |  | 40 |  | NguyenTCP | 2026-02-08 | 2026-02-08 |  |  | 2026-02-08 | 2026-02-09 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-08 | 2026-02-08 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-08 | 2026-02-09 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: Khanhvd Frontend: NguyenTCP | 2026-02-09 | 2026-02-12 |  |  | 2026-02-09 | 2026-02-10 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-24 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Completed
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Completed
2 | 1 |  | 1 |  | Logout | UI |  | 20 |  | NguyenTCP | 2026-02-08 | 2026-02-08 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-08 | 2026-02-08 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-09 | 2026-02-09 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: Khanhvd Frontend: NguyenTCP | 2026-02-10 | 2026-02-10 |  |  | 2026-02-10 | 2026-02-10 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 1900-01-25 04:48 |  | 100% |  |  | Completed
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Completed
3 | 1 |  | 1 |  | Forgot Password | UI |  | 30 |  | NguyenTCP | 2026-02-09 | 2026-02-10 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-09 | 2026-02-09 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-09 | 2026-02-09 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: Khanhvd Frontend: NguyenTCP | 2026-02-10 | 2026-02-12 |  |  | 2026-02-10 | 2026-02-10 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Completed
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Completed
4 | 1 |  | 1 |  | Profile Screen | UI |  | 60 |  | NguyenTCP | 2026-02-10 | 2026-02-10 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-10 | 2026-02-10 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-10 | 2026-02-11 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: Khanhvd Frontend: NguyenTCP | 2026-02-10 | 2026-02-14 |  |  | 2026-02-08 | 2026-02-08 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Completed
| 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Completed
5 | 1 |  | 1 |  | Change Password | UI |  | 30 |  | NguyenTCP | 2026-02-10 | 2026-02-10 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-10 | 2026-02-10 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-10 | 2026-02-10 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: Khanhvd Frontend: NguyenTCP | 2026-02-10 | 2026-02-13 |  |  | 2026-02-03 | 2026-02-04 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Processing
6 | 1 |  | 1,2,3 |  | Notification | UI |  | 60 |  | AnhNT | 2026-02-24 | 2026-02-24 |  |  | 2026-02-13 |  |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Thangvd | 2026-02-24 | 2026-02-24 |  |  | 2026-02-13 |  |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Thangvd | 2026-02-25 | 2026-02-25 |  |  | 2026-02-13 |  |  | 50% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: Thangvd Frontend: AnhNT | 2026-02-26 | 2026-02-28 |  |  | 2026-02-14 |  |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Thangvd | [7 empty] | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100% |  |  | Processing
7 | 1 |  | 1,2,3 |  | Audit log | UI |  | 100 |  | AnhNT | 2026-02-14 | 2026-02-15 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Thangvd | 2026-02-14 | 2026-02-14 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Thangvd | 2026-02-14 | 2026-02-14 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: ThangVD Frontend: AnhNT | 2026-02-15 | 2026-02-17 |  |  | 2026-02-03 | 2026-02-04 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Thangvd | [7 empty] | 100% |  |  | New
| 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100% |  |  | New
8 | 1 |  | 2,3 |  | Archive Old Transactions | UI |  | 100 |  | Anhnt | 2026-03-03 | 2026-03-03 |  |  | 2026-03-03 | 2026-03-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | 2026-03-03 |  |  |  | 2026-03-03 |  |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | 2026-03-03 |  |  |  | 2026-03-03 |  |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Frontend: Anhnt backend: Lamhp | 2026-03-03 |  |  |  | 2026-03-03 |  |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Lamhp | [7 empty] | 100% |  |  | New
| 6 |  |  |  |  | IT |  |  |  | Anhnt | [7 empty] | 100% |  |  | New
User Role Management
9 | 1 |  | 1 | User Role Management Feature | User Account Management Screen | UI |  | 60 |  | AnhNT | 2026-02-10 | 2026-02-10 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Thangvd | 2026-02-10 | 2026-02-11 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 3 |  |  |  |  | SDS |  |  |  | Thangvd | 2026-02-11 | 2026-02-11 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: Thangvd Frontend: AnhNT | 2026-02-10 | 2026-02-15 |  |  | 2026-02-09 | 2026-02-11 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Thangvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | New
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-25 |  |  | 2026-02-24 | 2026-02-25 |  | 100% |  |  | New
10 | Supplier Management
| 1 |  | 1 | Supplier Management | Supplier Management Screen | UI |  | 60 |  | NguyenTCP | 2026-02-14 | 2026-02-14 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-14 | 2026-02-14 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-14 | 2026-02-14 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: lamhp Frontend: NguyenTCP | 2026-02-16 | 2026-02-24 |  |  | 2026-02-09 | 2026-02-11 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | New
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-25 |  |  | 2026-02-24 | 2026-02-25 |  | 100% |  |  | New
11
| 1 |  | 1 |  | Embedded History Supplier Screen | UI |  | 30 |  | NguyenTCP | 2026-02-23 | 2026-02-23 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Processing
| 2 |  |  |  |  | SRS |  |  |  | Khanhvd | 2026-02-23 | 2026-02-23 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 3 |  |  |  |  | SDS |  |  |  | Khanhvd | 2026-02-23 | 2026-02-23 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Backend: lamhp Frontend: NguyenTCP | 2026-02-23 | 2026-02-24 |  |  | 2026-02-09 | 2026-02-11 |  | 100% |  |  | New
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | New
| 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-24 | 2026-02-25 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | New
12 | Inventory Management
| 1 |  | 2 | Inventory Management | Item Management Screen | UI |  | 80 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: KhanhVD Frontend: AnhNT, NguyenTCP | 2026-03-03 | 2026-03-05 |  |  | 2026-03-03 |  |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  | Khanhvd | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  |  | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | Processing
13
| 1 |  | 2 |  | Manage Units of Measure | UI |  | 40 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: ThangVD Frontend: AnhNT | 2026-03-03 | 2026-03-05 |  |  | 2026-03-03 |  |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  |  | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  |  | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | Processing
14
| 1 |  | 2 |  | Manage Item Parameter | UI |  | 40 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: KhanhVD Frontend: AnhNT | 2026-03-03 | 2026-03-05 |  |  | 2026-03-03 |  |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  |  | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  |  | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | Processing
15
| 1 |  | 2 |  | Manage Package Specification | UI |  | 40 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: KhanhVD Frontend: AnhNT | 2026-03-03 | 2026-03-05 |  |  | 2026-03-03 |  |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  |  | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  |  | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | Processing
16
| 1 |  | 2 |  | Manage Item Category | UI |  | 40 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: ThangVD Frontend: AnhNT | 2026-02-09 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-11 |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-02-24 | 2026-02-26 |  |  | 2026-03-23 | 2026-03-24 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  |  | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | Processing
17
| 1 |  | 2 |  | Brand Management | UI |  | 40 |  | AnhNT | 2026-03-02 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-02 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-02 | 2026-03-02 |  |  | 2026-03-03 | 2026-03-03 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: ThangVD Frontend: AnhNT | 2026-03-05 | 2026-03-06 |  |  | 2026-03-05 | 2026-03-06 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-23 | 2026-03-23 |  |  | 2026-03-23 | 2026-03-23 |  | 100%
| 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-23 | 2026-03-23 |  |  | 2026-03-23 | 2026-03-23 |  | 100%
18
| 1 |  | 2 |  | Import Items | UI |  | 50 |  | AnhNT | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-01 |  | 100% |  |  | Processing
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-02 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-02 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend: KhanhVD Frontend: AnhNT | 2026-02-09 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-11 |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  |  | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  |  | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100% |  |  | Processing
19
| 1 |  | 2 |  | Embedded History Receiver Screen | UI |  | 30 |  | AnhNT | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-01 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | [7 empty] | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | [7 empty] | 100%
| 4 |  |  |  |  | Coding |  |  |  | Backend: KhanhVD Frontend: AnhNT | [7 empty] | 100%
| 5 |  |  |  |  | UT | [11 empty] | 100%
| 6 |  |  |  |  | IT | [11 empty] | 100%
20 | Receiver Management
| 1 |  | 1 | Receiver Management | Receiver Management Screen | UI |  | 50 |  | NguyenTCP | 2026-02-24 | 2026-02-24 |  |  | 2026-02-03 | 2026-02-03 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | 2026-02-24 | 2026-02-24 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | 2026-02-24 | 2026-02-24 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | BackEnd: Lamhp FrontEnd: NguyenTCP | 2026-02-24 | 2026-02-28 |  |  | 2026-02-09 | 2026-02-11 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | Lamhp | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-02-24 | 2026-02-25 |  |  | 2026-02-24 | 2026-02-25 |  | 100% |  |  | Processing
21
| 1 |  | 2 |  | Embedded History Receiver Screen | UI |  | 40 |  | NguyenTCP | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-01 |  | 100% |  |  | Processing
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-01 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | 2026-03-01 | 2026-03-01 |  |  | 2026-03-01 | 2026-03-01 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | BackEnd: Lamhp FrontEnd: NguyenTCP | 2026-03-03 | 2026-03-06 |  |  | 2026-03-03 | 2026-03-06 |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  | Lamhp | 2026-03-16 | 2026-03-16 |  |  | 2026-03-16 | 2026-03-16 |  | 100% |  |  | Processing
| 6 |  |  |  |  | IT |  |  |  | NguyenTCP | 2026-03-16 | 2026-03-16 |  |  | 2026-03-16 | 2026-03-16 |  | 100% |  |  | Processing
22
Stock Adjustment Screen
| 1 |  | 2 | Stock Adjustment Screen | Stock Adjustment Management Screen | UI |  | 80 |  | AnhNT | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | Lamph | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | Lamph | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: Lamph | 2026-03-10 | 2026-03-11 |  |  | 2026-03-10 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | Lamph | [7 empty] | 100%
23 | 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100%
| 1 |  | 2 |  | Stock Adjustment Detail Screen | UI |  | 70 |  | AnhNT | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | Lamph | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | Lamph | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 | 2026-03-10 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: Lamph | 2026-03-10 | 2026-03-11 |  |  | 2026-03-10 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | Lamph | [7 empty] | 100%
24 | 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100%
| 1 |  | 2 |  | Embedded History Stock Adjustment Screen | UI |  | 30 |  | AnhNT | 2026-03-10 | 2026-03-10 |  |  | 2026-03-10 |  |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-10 | 2026-03-10 |  |  | 2026-03-02 |  |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-10 | 2026-03-10 |  |  | 2026-03-02 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: ThangVD | 2026-03-10 | 2026-03-11 |  |  | 2026-03-08 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD |  |  |  |  | 2026-03-23 |  |  | 100%
25 | 6 |  |  |  |  | IT |  |  |  | AnhNT |  |  |  |  | 2026-03-12 |  |  | 100%
Approval Management Feature
| 1 |  | 2 | Approval Management Feature | Approval Queue Management Screen | UI |  | 100 |  | AnhNT | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-06 | 2026-03-07 |  |  | 2026-03-06 | 2026-03-07 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-06 | 2026-03-07 |  |  | 2026-03-06 | 2026-03-07 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: ThangVD | 2026-03-06 | 2026-03-11 |  |  | 2026-03-10 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-12 | 2026-03-13 | [5 empty] | 0%
26 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-12 | 2026-03-14 | [5 empty] | 0%
Reporting and Dashboard Feature
| 1 |  | 3 | Reporting and Dashboard Feature | Dashboard Reporting Screen | UI |  | 80 |  | NguyenTCP | 2026-03-26 | 2026-03-26 |  |  | 2026-03-26 | 2026-03-26 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | [7 empty] | 100%
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | [7 empty] | 100%
| 4 |  |  |  |  | Coding |  |  |  | BackEnd: Lamhp FrontEnd: NguyenTCP | [7 empty] | 100%
| 5 |  |  |  |  | UT |  |  |  | Lamhp | [7 empty] | 100%
27 | 6 |  |  |  |  | IT |  |  |  | NguyenTCP | [7 empty] | 100%
| 1 |  | 3 |  | Schedule Report Export Screen | UI |  | 50 |  | NguyenTCP | 2026-03-26 | 2026-03-26 |  |  | 2026-03-26 | 2026-03-26 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | [7 empty] | 100%
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | [7 empty] | 100%
| 4 |  |  |  |  | Coding |  |  |  | BackEnd: Lamhp FrontEnd: NguyenTCP | [7 empty] | 100%
| 5 |  |  |  |  | UT |  |  |  | Lamhp | [7 empty] | 100%
28 | 6 |  |  |  |  | IT |  |  |  | NguyenTCP | [7 empty] | 100%
| 1 |  | 3 |  | Embedded History Reporting Screen | UI |  | 30 |  | NguyenTCP | 2026-03-26 | 2026-03-26 |  |  | 2026-03-26 | 2026-03-26 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | [7 empty] | 100%
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | [7 empty] | 100%
| 4 |  |  |  |  | Coding |  |  |  | BackEnd: Lamhp FrontEnd: NguyenTCP | [7 empty] | 100%
| 5 |  |  |  |  | UT |  |  |  | Lamhp | [7 empty] | 100%
29 | 6 |  |  |  |  | IT |  |  |  | NguyenTCP | [7 empty] | 100%
| 1 |  | 1 | Warehouse Management | Warehouse Management Screen | UI |  | 50 |  | AnhNT | 2026-02-15 | 2026-02-16 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-02-15 | 2026-02-15 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-02-15 | 2026-02-15 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-02-16 | 2026-02-22 |  |  | 2026-02-06 | 2026-02-10 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Processing
30 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Processing
| 1 |  | 1 |  | Warehouse history | UI |  | 50 |  | AnhNT | 2026-02-15 | 2026-02-16 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-02-15 | 2026-02-15 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-02-15 | 2026-02-15 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-02-16 | 2026-02-22 |  |  | 2026-02-06 | 2026-02-10 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-02-24 | 2026-02-26 |  |  | 2026-02-24 | 2026-02-26 |  | 100% |  |  | Processing
31 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Processing
| 1 |  | 1 |  | Warehouse Detail | UI |  | 50 |  | AnhNT | 2026-02-15 | 2026-02-16 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-02-15 | 2026-02-15 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-02-15 | 2026-02-15 |  |  | 2026-02-04 | 2026-02-04 |  | 100% |  |  | Processing
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-02-16 | 2026-02-22 |  |  | 2026-02-06 | 2026-02-10 |  | 100% |  |  | Completed
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-02-24 | 2026-02-26 |  |  | 2026-02-24 | 2026-02-26 |  | 100% |  |  | Processing
32 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-24 | 2026-02-24 |  |  | 2026-02-24 | 2026-02-24 |  | 100% |  |  | Processing
Release Request Management
| 1 |  | 2 | Release Request Management | Release Request Management Screen | UI |  | 90 |  | NguyenTCP | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100% |  |  | New
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-22 | 2026-02-23 |  |  | 2026-02-22 | 2026-02-23 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: Backend: ThangVD | 2026-03-25 | 2026-03-29 |  |  | 2026-03-25 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-29 | 2026-03-30 |  |  | 2026-03-29 |  |  | 100%
33 | 6 |  |  |  |  | IT |  |  |  | KhanhVD | 2026-03-29 | 2026-03-30 |  |  | 2026-03-29 |  |  | 100%
| 1 |  | 2 |  | Release Request Detail Screen | UI |  | 90 |  | NguyenTCP | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100% |  |  | New
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-22 | 2026-02-23 |  |  | 2026-02-22 | 2026-02-23 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: ThangVD | 2026-03-25 | 2026-03-29 |  |  | 2026-03-25 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-30 | 2026-03-30 |  |  | 2026-03-30 |  |  | 100%
34 | 6 |  |  |  |  | IT |  |  |  | KhanhVD | 2026-03-30 | 2026-03-30 |  |  | 2026-03-30 |  |  | 100%
| 1 |  | 2 |  | Embedded History Release Request Screen | UI |  | 30 |  | NguyenTCP | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 |  |  | 100% |  |  | New
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 |  |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-22 | 2026-02-23 |  |  | 2026-02-22 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: | 2026-03-25 | 2026-03-29 |  |  | 2026-03-25 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-30 | 2026-03-30 |  |  | 2026-03-30 |  |  | 100%
35 | 6 |  |  |  |  | IT |  |  |  | KhanhVD | 2026-03-30 | 2026-03-30 |  |  | 2026-03-30 |  |  | 100%
| 1 |  | 2 | GRN Management | GRN Management Screen | UI |  | 80 |  | NguyenTCP | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | Lamhp | 2026-03-06 |  |  |  | 2026-03-06 | 2026-03-06 |  | 100% |  |  | New
| 3 |  |  |  |  | SDS |  |  |  | Lamhp | 2026-03-06 |  |  |  | 2026-03-06 |  |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Frontend: NguyenTCP Backend: KhanhVD | 2026-03-07 | 2026-03-10 |  |  | 2026-03-07 | 2026-03-10 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | khanhvd | 2026-03-19 | 2026-03-22 |  |  | 2026-03-21 | 2026-03-22 |  | 100%
36 | 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100%
GDN Management
| 1 |  | 2 | GDN Management | GDN Management Screen | UI |  | 80 |  | NguyenTCP | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-06 |  |  |  | 2026-03-06 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: KhanhVD | 2026-03-07 | 2026-03-10 |  |  | 2026-03-07 | 2026-03-10 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-21 | 2026-03-22 |  |  | 2026-03-21 |  |  | 100%
37 | 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100%
| 1 |  | 2 |  | GDN Detail Screen | UI |  | 80 |  | NguyenTCP | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-06 |  |  |  | 2026-03-06 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: ThangVD | 2026-03-07 | 2026-03-10 |  |  | 2026-03-07 | 2026-03-10 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-21 | 2026-03-22 |  |  | 2026-03-21 |  |  | 100%
38 | 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100%
| 1 |  | 3 |  | Embedded History GDN Screen | UI |  | 40 |  | NguyenTCP | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-06 | 2026-03-06 |  |  | 2026-03-06 | 2026-03-06 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-06 |  |  |  | 2026-03-06 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: ThangVD | 2026-03-07 | 2026-03-10 |  |  | 2026-03-07 | 2026-03-10 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-21 | 2026-03-22 |  |  | 2026-03-21 |  |  | 100%
39 | 6 |  |  |  |  | IT |  |  |  | AnhNT | [7 empty] | 100%
| 1 |  | 3 | Inventory Tracking Feature | Inventory Monitoring Screen | UI |  | 70 |  | AnhNT | 2026-03-01 | 2026-03-02 |  |  | 2026-03-01 | 2026-03-01 |  | 100% |  |  | New
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-02 | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-02 | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-03-08 | 2026-03-09 |  |  | 2026-03-08 | 2026-03-08 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-23 | 2026-03-25 |  |  | 2026-03-23 | 2026-03-23 |  | 100%
40 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-12 | 2026-03-12 |  |  | 2026-03-12 | 2026-03-12 |  | 100%
| 1 |  | 3 |  | Embedded History Inventory Screen | UI |  | 30 |  | AnhNT | 2026-03-01 | 2026-03-02 |  |  | 2026-03-01 | 2026-03-01 |  | 100% |  |  | New
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-02 | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-02 | 2026-03-04 |  |  | 2026-03-02 | 2026-03-02 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-03-08 | 2026-03-09 |  |  | 2026-03-08 | 2026-03-08 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-23 | 2026-03-25 |  |  | 2026-03-23 | 2026-03-23 |  | 100%
41 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-12 | 2026-03-12 |  |  | 2026-03-12 | 2026-03-12 |  | 100%
Stocktaking Management Feature
| 1 |  | 2 | Stocktaking Management Feature | Stocktaking Management Screen | UI |  | 100 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-02-09 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-11 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100%
42 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100%
| 1 |  | 2 |  | Embedded History Stocktaking Screen | UI |  | 40 |  | AnhNT | 2026-02-02 | 2026-02-03 |  |  | 2026-02-03 | 2026-02-03 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-02-03 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Backend : ThangVD Frontend: AnhNT | 2026-02-09 | 2026-02-10 |  |  | 2026-02-09 | 2026-02-11 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-02-24 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100%
43 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-02-13 | 2026-02-13 |  |  | 2026-02-13 | 2026-02-13 |  | 100%
| 1 |  | 3 |  | System Control Screen | UI |  | 30 | [9 empty] | 100%
| 2 |  |  |  |  | SRS | [11 empty] | 100%
| 3 |  |  |  |  | SDS | [11 empty] | 100%
| 4 |  |  |  |  | Coding | [11 empty] | 100%
| 5 |  |  |  |  | UT | [11 empty] | 100%
44 | 6 |  |  |  |  | IT | [11 empty] | 100%
Inventory Costing / Valuation
| 1 |  | 2 | Inventory Costing / Valuation | Inventory Costing and Valuation Screen | UI |  | 80 |  | NguyenTCP | 2026-03-15 | 2026-03-15 |  |  | 2026-03-15 | 2026-03-15 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-15 | 2026-03-15 |  |  | 2026-03-15 | 2026-03-15 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-03-15 | 2026-03-15 |  |  | 2026-03-15 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: NguyenTCP Backend: KhanhVD | 2026-03-15 | 2026-03-23 |  |  | 2026-03-15 | 2026-03-23 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | KhanhVD | 2026-03-24 |  |  |  | 2026-03-24 |  |  | 100%
45 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-24 |  |  |  | 2026-03-24 |  |  | 100%
| 1 |  | 2 | Purchase Order Management | Purchase Order Management | UI |  | 60 |  | NguyenTCP | 2026-02-26 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | Completed
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-26 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100% |  |  | New
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-26 | 2026-02-26 |  |  | 2026-02-26 |  |  | 100% |  |  | New
| 4 |  |  |  |  | Coding |  |  |  | Frontend: NguyenTCP Backend: KhanhVD | 2026-02-26 | 2026-03-31 |  |  | 2026-02-26 | 2026-03-31 |  | 100% |  |  | Processing
| 5 |  |  |  |  | UT |  |  |  | KhanhVD | 2026-03-15 | 2026-03-20 |  |  | 2026-03-18 | 2026-03-19 |  | 100% |  |  | New
46 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-21 |  |  |  | 2026-03-21 |  |  | 100% |  |  | New
| 1 |  | 2 |  | Embedded history | UI |  | 40 |  | NguyenTCP | 2026-02-28 | 2026-02-28 |  |  | 2026-02-28 | 2026-02-28 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-02-26 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-02-26 | 2026-02-26 |  |  | 2026-02-26 | 2026-02-26 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: NguyenTCP Backend: KhanhVD | 2026-02-28 | 2026-03-05 |  |  | 2026-02-28 | 2026-03-05 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | KhanhVD | 2026-03-05 | 2026-03-06 |  |  | 2026-03-05 | 2026-03-06 |  | 100%
47 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-05 | 2026-03-06 |  |  | 2026-03-05 | 2026-03-06 |  | 100%
| 1 |  | 2 | Purchase Return Management | Purchase Return Management Screen | UI |  | 80 |  | AnhNT | 2026-03-07 | 2026-03-07 |  |  | 2026-03-07 | 2026-03-07 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-07 | 2026-03-08 |  |  | 2026-03-07 | 2026-03-08 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-03-07 | 2026-03-08 |  |  | 2026-03-07 | 2026-03-08 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: KhanhVD | 2026-03-07 | 2026-03-11 |  |  | 2026-03-07 | 2026-03-12 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | KhanhVD | 2026-03-12 |  |  |  | 2026-03-13 |  |  | 100%
48 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-12 |  |  |  | 2026-03-13 |  |  | 100%
| 1 |  | 2 |  | Purchase Return Detail Screen | UI |  | 80 |  | NguyenTCP | 2026-03-07 | 2026-03-07 |  |  | 2026-03-07 | 2026-03-07 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-07 | 2026-03-08 |  |  | 2026-03-07 | 2026-03-08 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-03-07 | 2026-03-08 |  |  | 2026-03-07 | 2026-03-08 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: KhanhVD | 2026-03-07 | 2026-03-11 |  |  | 2026-03-07 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | KhanhVD | 2026-03-12 |  |  |  | 2026-03-13 |  |  | 100%
49 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-12 |  |  |  | 2026-03-13 |  |  | 100%
| 1 |  | 2 |  | Purchase Return Embedded history | UI |  | 30 |  | NguyenTCP | 2026-03-07 | 2026-03-07 |  |  | 2026-03-07 | 2026-03-07 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | KhanhVD | 2026-03-07 | 2026-03-08 |  |  | 2026-03-07 | 2026-03-08 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | KhanhVD | 2026-03-07 |  |  |  | 2026-03-07 |  |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: KhanhVD | 2026-03-07 |  |  |  | 2026-03-07 |  |  | 100%
| 5 |  |  |  |  | UT |  |  |  | KhanhVD | 2026-03-12 |  |  |  | 2026-03-13 |  |  | 100%
50 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-12 |  |  |  | 2026-03-13 |  |  | 100%
Shipping Feature
| 1 |  | 3 | Shipping Management | Shipping Management Screen | UI |  | 30 |  | AnhNT | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100%
| 2 |  |  |  |  | SRS |  |  |  | ThangVD | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100%
| 3 |  |  |  |  | SDS |  |  |  | ThangVD | 2026-03-19 | 2026-03-19 |  |  | 2026-03-19 | 2026-03-19 |  | 100%
| 4 |  |  |  |  | Coding |  |  |  | Frontend: AnhNT Backend: ThangVD | 2026-03-19 | 2026-03-21 |  |  | 2026-03-19 | 2026-03-21 |  | 100%
| 5 |  |  |  |  | UT |  |  |  | ThangVD | 2026-03-21 | 2026-03-21 | [5 empty] | 100%
51 | 6 |  |  |  |  | IT |  |  |  | AnhNT | 2026-03-21 | 2026-03-21 |  |  | 2026-03-21 |  |  | 100%
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
Note on O1: ====== ID#AAABl2wetA4 Anh Nguyen The (2025-06-15 07:22:54) Input report date here to adjust Plan Progress

## Configure
Ratio
UI | 0.05
SRS | 0.1
SDS | 0.1
Coding | 0.5
UT | 0.1
IT | 0.15

## Defects
Date | Defect ID | Defect Description | Activity | Product | Product Details | Assigner | Assignee | Status | Updated | Notes
2025-10-09 | D-RP01 | The system did not send any SMS message containing an OTP for resetting password until many hours later | IT | Report 5.2 | Integration Test, Authentication |  |  | Fixed
2025-10-09 | D-RP05 | Strange error occured when trying to log in after cancelling password reset | IT | Report 5.2 | Integration Test, Authentication |  |  | Fixed
2025-10-09 | D-AM01 | Texts were in an intelligible color (white) | IT | Report 5.2 | Integration Test, Director |  |  | Fixed
2025-10-09 | D-AM02 | Could not view account details | IT | Report 5.2 | Integration Test, Director |  |  | Fixed
2025-10-09 | D-AM06 | Phone number validation didn't work as intended | IT | Report 5.2 | Integration Test, Director |  |  | Fixed
2025-10-09 | D-AM10 | Feature not implemented | IT | Report 5.2 | Integration Test, Director |  |  | Fixed
2025-10-14 | D-VN02 | Notifications were not marked as read | IT | Report 5.2 | Integration Test, Notifications |  |  | Fixed
2025-10-14 | D-SN01 | Actions did not send notifications | IT | Report 5.2 | Integration Test, Notifications |  |  | Fixed
2025-11-29 | D-TS03 | Button was not functional | IT | Report 5.2 | Integration Test, TechnicalStaff |  |  | Fixed
2025-11-29 | D-TS04 | Button was not functional | IT | Report 5.2 | Integration Test, TechnicalStaff |  |  | Fixed
2025-11-29 | D-TS05 | Button was not functional | IT | Report 5.2 | Integration Test, TechnicalStaff |  |  | Fixed
2025-11-29 | D-TS06 | ODBC error | IT | Report 5.2 | Integration Test, TechnicalStaff |  |  | Fixed
2025-11-29 | D-TS07 | Button not found | IT | Report 5.2 | Integration Test, TechnicalStaff |  |  | Fixed
2025-11-29 | D-TS08 | Database interaction error | IT | Report 5.2 | Integration Test, TechnicalStaff |  |  | Fixed
2025-12-09 | D-PM09 | No QR code generated | IT | Report 5.2 | Integration Test, ProductionManager |  |  | Fixed
2025-12-09 | D-PM12 | The option for 10 stamps shouldn't have available when there weren't enough cavities | IT | Report 5.2 | Integration Test, ProductionManager |  |  | Fixed
2025-12-09 | D-ACC02 | No validation for non-empty name input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC03 | No validation for non-empty email input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC04 | No validation for valid email input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC05 | No validation for non-empty phone number input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC06 | No validation for valid phone number input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC07 | No validation for numerical string input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC08 | No validation for unique email input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ACC09 | No validation for unique phone number input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC02 | No validation for non-empty name input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC03 | No validation for valid email input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC04 | No validation for non-empty email input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC05 | No validation for valid phone number input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC06 | No validation for non-empty phone number input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC07 | No validation for numerical string input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC08 | No validation for unique email input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECC09 | No validation for unique phone number input | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-DCC01 | The button for deleting did not delete | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-ECR02 | Page not implemented | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-09 | D-IM05 | Could not view material details | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed
2025-12-09 | D-IM06 | Mismatched page labels | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed
2025-12-09 | D-IM07 | Mismatched page labels | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed
2025-12-09 | D-IM08 | Could not view request details | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed
2025-12-09 | D-IM10 | Button was not functional | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed
2025-12-09 | D-IM11 | Button was not functional | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed
2025-12-09 | D-VD01 | Could not view document: no file, only path | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-10 | D-ECR02-2 | No customers could be chosen for edit | IT | Report 5.2 | Integration Test, SaleManager |  |  | Fixed
2025-12-10 | D-IM10-2 | Content displayed on the wrong page | IT | Report 5.2 | Integration Test, InventoryManager |  |  | Fixed

## config (hidden)
Redmine Synchronous Configuration
Redmine Information |  | Update Column Setting
URL | http://qnet-carp.css.exnet.fujitsu.co.jp/ | Tracker | Yes
Project Id |  | WBS | No
Query ID |  | Task Detail | Yes
Rest Key | access_key.json | Notes | Yes
WBS Information |  | Man-Day | Yes
Allow Create New Task | Only Child | Assigned To | Yes
Fill Actual Date | Yes | Plan Start Date | Yes
Remove old highlight |  | Plan End Date | Yes
Child Level | 6 | Actual Start Date | Yes
New Status | New,新規 | Actual End Date | Yes
Closed Status | Completed,Rejected,終了,却下 | Actual Progress | Yes
Display Holiday JP | On | Status | Yes
Display Holiday VN | On | Priority | Yes
Remove Prefix | [AKS],[MICX],[SBE],[AutoTest],[Recall] | Main PIC | Yes
Note tag | #Note: | Plan Review End Date | Yes
|  | Actual Review End Date | Yes
|  | Release Date | Yes

## Data (hidden)
Progress
Status | %Progress | Meaning | Activity
Assigned | %Done = 10 | Prepare | Work
Assigned | 10 <= %Done < 70 | In working | Work
Resolved | %Done = 70 | Finish work | Work
Resolved | 70 <= %Done <= 80 | Review | Review
Resolved | 80 <= %Done <= 90 | Rework | Rework
Closed | %Done = 100 | Task's done | Work
10%
20%
30%
40%
50%
60%
70%
80%
90%
100%

## vacation_dates (hidden)
Japan |  | Vietnam |  | Personal Vacation
2021-01-01 | 元日 | 2021-01-01 | New Year's Day
2021-01-11 | 成人の日 | 2021-02-10 | Tet Holiday
2021-02-11 | 建国記念の日 | 2021-02-11 | Tet Eve
2021-02-23 | 天皇誕生日 | 2021-02-12 | Tet
2021-03-20 | 春分の日 | 2021-02-13 | Tet
2021-04-29 | 昭和の日 | 2021-02-14 | Tet
2021-05-03 | 憲法記念日 | 2021-02-15 | Tet
2021-05-04 | みどりの日 | 2021-02-16 | Tet
2021-05-05 | こどもの日 | 2021-04-21 | Hung King's Template Festival
2021-07-22 | 海の日 | 2021-04-30 | Reunification Day
2021-07-23 | スポーツの日 | 2021-05-01 | Labour Day
2021-08-08 | 山の日 | 2021-05-03 | Labour Day
2021-08-09 | 振替休日 | 2021-09-02 | National Day
2021-09-20 | 敬老の日 | 2021-09-03 | National Day
2021-09-23 | 秋分の日 | 2021-09-04 | National Day
2021-11-03 | 文化の日 | 2021-09-05 | National Day
2021-11-23 | 勤労感謝の日 | 2022-01-01 | New Year's Day
2021-12-27 | 年末年始の日 | 2022-01-03 | New Year's Day
2021-12-28 | 年末年始の日 | 2022-01-31 | Tet
2021-12-29 | 年末年始の日 | 2022-02-01 | Tet
2021-12-30 | 年末年始の日 | 2022-02-02 | Tet
2021-12-31 | 年末年始の日 | 2022-02-03 | Tet
2022-01-03 | 年末年始の日 | 2022-02-04 | Tet
2022-01-04 | 年末年始の日 | 2022-04-10 | Hung King's Template Festival
2022-01-05 | 年末年始の日 | 2022-04-11 | Hung King's Template Festival
2022-01-01 | 元日 | 2022-04-30 | Reunification Day
2022-01-10 | 成人の日 | 2022-05-01 | Labour Day
2022-02-11 | 建国記念の日 | 2022-05-02 | Reunification Day
2022-02-23 | 天皇誕生日 | 2022-05-03 | Labour Day
2022-03-21 | 春分の日 | 2022-09-01 | National Day
2022-04-29 | 昭和の日 | 2022-09-02 | National Day
2022-05-03 | 憲法記念日
2022-05-04 | みどりの日
2022-05-05 | こどもの日
2022-07-18 | 海の日
2022-08-11 | 山の日
2022-09-19 | 敬老の日
2022-09-23 | 秋分の日
2022-10-10 | スポーツの日
2022-11-03 | 文化の日
2022-11-23 | 勤労感謝の日

## ComboBox (hidden)
Status
New
Feedback
Processing
Modifying
Resolved
Re-Open
Verifying
Completed
Rejected
Pending